## CoC Board
DRAFT: CoC Board Annual Workplan
Updated 6/24/24 | Lead | 2024-05-01 |  |  |  | 2024-06-01 |  |  |  | 2024-07-01 |  |  |  |  | 2024-08-01 |  |  |  | 2024-09-01 |  |  |  |  | 2024-10-01 |  |  |  | 2024-11-01 |  |  |  | 2024-12-01 |  |  |  |  | 2025-01-01 |  |  |  | 2025-02-01 |  |  |  | 2025-03-01
X = In Progress/Upcoming Task or Event; C=Complete |  | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 5
Organizing the Board
Determine frequency and location of meetings | bar: 2024-05-01 1; 2024-07-01 4
Develop transparent process to access materials | bar: 2024-06-01 2
Determine the board voting structure | bar: 2024-06-01 3 to 2024-06-01 4
Determine how agendas will be prepared and structured | bar: 2024-06-01 4
Develop a board communications protocol and associated templates | bar: 2024-06-01 4 to 2024-07-01 4
Establish and/or revisit guiding principles | bar: 2024-06-01 4; 2024-07-01 3
Identify roles/job descriptions for board leadership | bar: 2024-07-01 4
Elect Board Leadership | bar: 2024-09-01 2; 2024-09-01 4
Develop Board Policies/Procedures (Bylaws) - conflict of interest policy | Lisa and Miguel (Angela staff support) | bar: 2024-06-01 4 to 2024-07-01 4; 2024-08-01 1 to 2024-08-01 4
Board skills and representation matrix | bar: 2024-07-01 4
Identify board members to task specific roles/build specific expertise | bar: 2024-08-01 4
Create annual board work plan | bar: 2024-06-01 4 to 2024-08-01 3
Identifying Board Priorities (suggestion: before next NOFO process)
Review CoC Board representation | bar: 2024-09-01 2
Determine what an annual board evaulation process looks like | bar: 2024-11-01 2
Board Training
CoC Operations, Roles & Responsibilities Training | bar: 2024-06-01 2; 2024-06-01 4
A healthy homeless services system | bar: 2024-07-01 4
Housing affordability and the homeless services system | bar: 2024-07-01 4
Data sources and required reports - what they do and do not tell us | bar: 2024-09-01 3 to 2024-09-01 4
Collaborative Applicant Responsibilities Training (distinguish roles) | bar: 2024-08-01 2
HMIS Lead Responsibilities Training | bar: 2024-08-01 2
Coordinated Entry Training | bar: 2024-07-01 4
Peer to Peer Learning with high functioning CoC Boards
Review CoC Governance Charter and CoC Recommendations
Homelessness response funding streams | bar: 2024-09-01 3 to 2024-09-01 4
CoC funding - overview of current funding portfolio | bar: 2024-08-01 2; 2024-09-01 3 to 2024-09-01 4
Special CoC funding, scope and expectations | bar: 2024-08-01 2; 2024-09-01 3 to 2024-09-01 4
Review current CoC Budget and awarded projects | bar: 2024-11-01 2; 2024-12-01 2
Create a plan for ongoing training and education | bar: 2024-10-01 3 to 2024-10-01 4
Local Governance and Oversight
CoC Member Mtgs | [37 empty] | x | bar: 2024-07-01 2; 2024-09-01 2; 2024-11-01 2
Determine what board support is needed for CoC membership | bar: 2024-07-01 4; 2024-08-01 2
Determine what support is needed for CoC Core Function Committees | bar: 2024-07-01 4; 2024-08-01 2; 2024-09-01 2 to 2024-10-01 2
Special CoC funding sources & board support/oversight for implementation | bar: 2024-09-01 2 to 2024-10-01 2
Determine which decisions can be made by committees and which need to come before the board | bar: 2024-09-01 2 to 2024-10-01 2
Draft and finalize a Collaborative Applicant MOU | [37 empty] | x | bar: 2024-12-01 1 to 2024-12-01 4
Draft and finalize an HMIS Lead MOU | [37 empty] | x | x | x | x | x
Draft and finalize a CE Lead Entity MOU | [37 empty] | x | x | x | x | x
Board Annual Activities
Develop an annual calendar of CoC activities | [36 empty] | x | bar: 2024-12-01 2 to 2024-12-01 5
Review & Update Governance Charter | [36 empty] | x | x | bar: 2024-12-01 2 to 2024-12-01 5
Determine what board support is needed | [36 empty] | x | x | bar: 2024-12-01 2 to 2024-12-01 5
Request & Review CoC Quarterly Spend Down Report | bar: 2024-06-01 3
Quarterly Review of Workplan | [36 empty] | x | bar: 2024-09-01 1 to 2024-09-01 2; 2024-10-01 2
Develop Annual Workplan | [36 empty] | x | x | x | x | x | x | x | x | x | x | x | x
CoC Competition Activities
Approve local application funding priorities | [40 empty] | x | x | x | x | x | x | x | x | x
Establish local competition policies and procedures (March-ish) | [40 empty] | x | x | x | x | x | x | x | x | x
Designate entity to recruit the scoring and ranking team (6/24) | [40 empty] | x | x | x | x | x | x | x | x | x
Formally approve the Priority Listing and Consolidated Application submission to HUD (usually September) | [40 empty] | x | x | x | x | x | x | x | x | x
HUD-Required Reporting
Review LSA report prior to submission | bar: 2024-10-01 1 to 2024-11-01 4
Review System Performance Measures Report prior to submission | bar: 2024-10-01 1 to 2024-11-01 4
Review PIT and HIC data reports prior to submission | [44 empty] | x | x | x | x | x
Lead Entity Oversight
Review Collaborative Applicant Annual Performance Report (APR) | [40 empty] | x | x | x | x | x | x | x | x | x
Review HMIS Annual Performance Report (APR) | bar: 2024-07-01 4 to 2024-08-01 4
Review Collaborative Applicant annual budget and planning grant budget | [40 empty] | x | x | x | x | x | x | x | x | x | bar: 2024-11-01 2; 2024-12-01 2
Review HMIS annual budget | [40 empty] | x | x | x | x | x | x | x | x | x
Review Coordinated Entry Lead Entity budgets | [40 empty] | x | x | x | x | x | x | x | x | x
Monitor Collaborative Applicant (including input from CoC Programs Committee and associated contractors) | [40 empty] | x | x | x | x | x | x | x | x | x
Monitor HMIS Lead (including input from HMIS Steering Committee and associated contractors) | [40 empty] | x | x | x | x | x | x | x | x | x
Monitor Coordinated Entry Lead Entity (including input from Coordinated Services Committee and associated contractors) | [40 empty] | x | x | x | x | x | x | x | x | x
CoC Planning
Reporting deadlines | bar: 2024-11-01 2; 2024-12-01 2
PIT Count
Create Funding Portfolio for Homelessness Response and Review Gaps and Needs | [41 empty] | x | x | x | x | x | x | x
Consolidated planning and CAPER

## CoC Programs
DRAFT: CoC Programs Committee Workplan
Updated: | Lead | 2024-05-01 |  |  |  | 2024-06-01 |  |  |  | 2024-07-01 |  |  |  |  | 2024-08-01 |  |  |  | 2024-09-01 |  |  |  |  | 2024-10-01 |  |  |  | 2024-11-01 |  |  |  | 2024-12-01 |  |  |  |  | 2025-01-01 |  |  |  | 2025-02-01 |  |  |  | 2025-03-01
X = In Progress/Upcoming Task or Event; C=Complete |  | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 5
Committee Start-up
Determine frequency and location of meetings | bar: 2024-07-01 2
Develop transparent process to access materials | bar: 2024-06-01 2
Determine the voting structure | bar: 2024-06-01 2
Determine how agendas will be prepared and structured | bar: 2024-06-01 2; 2024-07-01 4
Develop a communications protocol with other committees
Establish guiding principles | bar: 2024-08-01 2; 2024-08-01 4
Identify roles/job descriptions for leadership and staff | bar: 2024-07-01 2
Elect Leadership | bar: 2024-07-01 4
Review CoC standards and update, present to board for adoption (with monitoring collab)
Identify board members to task specific roles/build specific expertise
Create annual work plan
Determine what an annual committee self-evaulation process looks like including skills & representation
Training for Committee Members
CoC Operations, Roles & Responsibilities Training | bar: 2024-06-01 2
A healthy homeless services system
Housing affordability and the homeless services system
Data sources and required reports - what they do and do not tell us | bar: 2024-09-01 2; 2024-09-01 4
CoC monitoring requirements and approaches
Collaborative Applicant Responsibilities Training (distinguish roles)
Coordinated Entry Training
Review CoC Governance Charter and CoC Recommendations
Homelessness response funding streams
CoC funding - overview of current funding portfolio
Special CoC funding, scope and expectations (Unsheltered SNOFO 2025)
Current CoC Budget and awarded projects
Create a plan for ongoing training and education (including onboarding for new members)
Local Governance and Oversight
CoC Member Mtgs - attend and report | [37 empty] | x | bar: 2024-07-01 2; 2024-09-01 2; 2024-11-01 2
Determine what is needed to inform, support and empower CoC membership
Review and make recommendations on the CoC Board's CA Lead Entity MOU
Annual Activities
Review & suggest updates to the governance charter from the committee perspective, as part of the annual update
Annual Planning grant budget report
Monitor Collaborative Applicant (with board)
Work with ESG recipients to create an annual plan for ESG-CoC coordination to propose to the CoC Board
Consolidated planning and CAPER
Review LSA report prior to submission
Review CA APR
Review CA annual budget
Annual Activities - CoC Project Monitoring & Evaluation
Develop a communications plan to notify recipients
Annual Activities - CoC Competition
Role in priotiy Listing and Consolidated Application submission to HUD (usually September)? | bar: 2024-09-01 1 to 2024-09-01 2
Update local application process and priorities
Help recruit the scoring and ranking team | bar: 2024-06-01 3
Identify community training needed to improve NOFO scoring and response and share it with the coordinated services committee (5/1-4/30 yearly)

## Coordinated Services
DRAFT: Coordinated Services Committee Workplan
Updated: | Lead | 2024-05-01 |  |  |  | 2024-06-01 |  |  |  | 2024-07-01 |  |  |  |  | 2024-08-01 |  |  |  | 2024-09-01 |  |  |  |  | 2024-10-01 |  |  |  | 2024-11-01 |  |  |  | 2024-12-01 |  |  |  |  | 2025-01-01 |  |  |  | 2025-02-01 |  |  |  | 2025-03-01
X = In Progress/Upcoming Task or Event; C=Complete |  | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 5
Committee Start-up
Determine frequency and location of meetings | bar: 2024-07-01 4
Develop transparent process to access materials | bar: 2024-06-01 2
Determine the voting structure | bar: 2024-06-01 3
Determine how agendas will be prepared and structured | bar: 2024-06-01 4
Develop a communications protocol and associated templates | bar: 2024-06-01 4 to 2024-07-01 4
Establish guiding principles | bar: 2024-06-01 4; 2024-07-01 3
Identify roles/job descriptions for leadership and staff | bar: 2024-07-01 2; 2024-07-01 4
Elect Leadership | bar: 2024-09-01 4
Establish committee bylaws) - including a conflict of interest policy | bar: 2024-06-01 4 to 2024-07-01 4; 2024-08-01 1 to 2024-08-01 4
Skills and representation matrix | bar: 2024-07-01 4
Identify board members to task specific roles/build specific expertise | bar: 2024-08-01 4
Create annual work plan | bar: 2024-06-01 4 to 2024-08-01 3
Determine what an annual committee self-evaulation process looks like
Training
CoC Operations, Roles & Responsibilities Training | bar: 2024-06-01 2; 2024-06-01 4; 2024-07-01 2 to 2024-07-01 3
A healthy homeless services system | bar: 2024-08-01 3
Housing affordability and the homeless services system | bar: 2024-08-01 3
Data sources and required reports - what they do and do not tell us | bar: 2024-09-01 3 to 2024-09-01 4
Collaborative Applicant Responsibilities Training (distinguish roles) | bar: 2024-07-01 2
HMIS Lead Responsibilities Training | bar: 2024-07-01 2
Coordinated Entry Training | bar: 2024-07-01 4
Review CoC Governance Charter and CoC Recommendations | bar: 2024-07-01 4
Homelessness response funding streams | bar: 2024-09-01 3 to 2024-09-01 4
CoC funding - overview of current funding portfolio | bar: 2024-09-01 3 to 2024-09-01 4
Special CoC funding, scope and expectations | bar: 2024-09-01 3 to 2024-09-01 4
Review current CoC Budget and awarded projects
Create a plan for ongoing training and education | bar: 2024-10-01 3 to 2024-10-01 4
Local Governance and Oversight
CoC Member Mtgs - attend and report | [37 empty] | x | bar: 2024-07-01 2; 2024-09-01 2; 2024-11-01 2
Determine what is needed to inform, support and empower CoC membership
Review and make recommendations on the CoC Board's CE Lead Entity MOU
Determine which decisions can be made by committees and which need to come before the board
CoC Board Mtgs - attend and report
Annual Activities
Review & Update Governance Charter
Team up with board to monitor CE Lead Entity
CES P&P updates | bar: 2024-09-01 1 to 2024-09-01 2
Frontline learning collaborative support and planning
Provider training expectations, support and planning
Build inventory of existing training
CE timeline review (PJ and Tanesha project management plan)
Review CE APR
Provider compensation standards
Data that need to be reviewed and tracked Program denials
Develop process to monitor agencies on coordinated entry
CE Lead onboarding and partnership definitions

## HMIS Steering
DRAFT: HMIS Steering Committee Workplan
Updated: | Lead | 2024-05-01 |  |  |  | 2024-06-01 |  |  |  | 2024-07-01 |  |  |  |  | 2024-08-01 |  |  |  | 2024-09-01 |  |  |  |  | 2024-10-01 |  |  |  | 2024-11-01 |  |  |  | 2024-12-01 |  |  |  |  | 2025-01-01 |  |  |  | 2025-02-01 |  |  |  | 2025-03-01 |  |  |  |  | 2025-04-25
X = In Progress/Upcoming Task or Event; E=Expected Deadline D=Deadline; C=Complete |  | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4
Committee Meeting Schedule | bar: 2024-05-01 1 to 2024-12-01 5
Committee Start-up
Determine frequency and location of meetings | bar: 2024-07-01 4
Develop transparent process to access materials | bar: 2024-06-01 2
Determine the voting structure | bar: 2024-06-01 3
Determine how agendas will be prepared and structured | bar: 2024-07-01 5
Develop a communications protocol and associated templates | bar: 2024-06-01 4 to 2024-07-01 4; 2024-08-01 2
Establish guiding principles
Identify roles/job descriptions for leadership and staff | bar: 2024-07-01 2; 2024-07-01 4
Elect Leadership | bar: 2024-07-01 4
Skills and representation matrix
Identify Committee members to task specific roles/build specific expertise | bar: 2024-08-01 4
Create annual work plan | bar: 2024-08-01 3
Determine what an annual committee self-evaulation process looks like
Training
CoC Operations, Roles & Responsibilities Training | bar: 2024-06-01 2; 2024-06-01 4; 2024-07-01 2
A healthy homeless services system | bar: 2024-08-01 3
Housing affordability and the homeless services system | bar: 2024-08-01 3
Data sources and required reports - what they do and do not tell us | bar: 2024-09-01 3 to 2024-09-01 4
Collaborative Applicant Responsibilities Training (distinguish roles) | bar: 2024-07-01 2
HMIS Lead Responsibilities Training | bar: 2024-07-01 2
Coordinated Entry Training | bar: 2024-07-01 4
Review CoC Governance Charter and CoC Recommendations | bar: 2024-07-01 4
Homelessness response funding streams and HMIS | bar: 2024-09-01 3 to 2024-09-01 4
CoC funding - overview of current funding portfolio | bar: 2024-09-01 3 to 2024-09-01 4
Special CoC funding, scope and expectations | bar: 2024-09-01 3 to 2024-09-01 4
Review current CoC Budget and awarded projects
Create a plan for ongoing training and education | bar: 2024-10-01 3 to 2024-10-01 4
Local Governance and Oversight
CoC Member Mtgs - attend and report | [37 empty] | x | bar: 2024-07-01 2; 2024-09-01 2; 2024-11-01 2
Determine what is needed to inform, support and empower CoC membership
Review and make recommendations on the CoC Board's HMIS Lead MOU
Review and update HMIS new user agency/license application | bar: 2024-09-01 2 to 2024-10-01 2
Annual Activities
Conduct an annual committee self-evaluation process
Review Annual HMIS budget and report any concerns or recommendations to the CoC Board
Collaborate with CoC board on annual HMIS Lead monitoring and evaluation
Review and update HMIS Standard Operating Procedures and Governance Docs (and any other applicable docs)
Review LSA report prior to submission | [36 empty] | X | E | bar: 2024-11-01 1 to 2024-12-01 5
Review HMIS APR | bar: 2024-07-01 1 to 2024-07-01 2
Review System Performance Measures (SPMs) prior to submission | [41 empty] | X | X | X | X | E |  |  |  |  | X | X | X
Analyze System Performance Measures (SPMs); discuss themes/trends
Implementation plan for new data standards (prep for 2027)
Support planning of PIT/HIC in conjunction with the Programs Committee | [36 empty] | X | X | X | E | bar: 2024-11-01 1 to 2024-12-01 5
Review PIT/HIC data prior to submission | [46 empty] | X | X | E
Analyze PIT/HIC results
Ensure PIT/HIC results are reported to the board, membership, other committees, and community partners